## Slide 1
AGILE / SCRUM | SPRINT PLANNING
Hospital Management System (HMS)
Sprint 1: 19 Oct 2026 to 01 Nov 2026
Muhammad Abdullah Malik | Umair Qaisar | Talha Azeem | Waleed Ali | Muhammad Yousaf
Notes: Presenter: Muhammad Abdullah Malik. Introduce the team and say the presentation will be done live in the project management tool.

## Slide 2
1. Project overview
Objectives
Replace paper / separate tools with one system for patients, doctors, appointments, records, bills and medicines.
Keep data correct with three validation layers: browser, Python server, database constraints.
Give staff dashboard, alerts, search and reports so they can see what needs attention.
Prove quality with automatic tests (86 API checks, 48 schema checks, 44 browser checks).
browser (HMS/) > server.py > SQLite (hms.db)
Major modules
Patient Management
Register, search, edit, view patients and their history
Doctor Management
Doctor records, departments, weekly schedules, fees
Appointments
Booking with slots, double-booking prevention, week calendar
Medical Records
Visits, diagnosis, vitals, prescriptions, follow-ups
Billing
Invoices with live totals, discount, tax, payment status
Pharmacy
Medicine stock, expiry warnings, dispensing
Supporting
Login, dashboard, reports, notifications, global search, audit log
Notes: Presenter: Abdullah. HMS = browser -> Python server -> SQLite database. Three validation layers.

## Slide 3
2. Scrum team and roles
A
Muhammad Abdullah Malik
Scrum Master + Developer (Team Lead)
Runs Sprint ceremonies, removes blockers, keeps the board current. Builds database, server.py, login, audit log and API tests.
U
Umair Qaisar
Product Owner + Developer
Owns and prioritises the Product Backlog, writes acceptance criteria, accepts finished stories. Builds Patient module, login page and global search.
T
Talha Azeem
Developer
Builds Doctor Management and Appointments (booking, slots, calendar, double-booking warning).
W
Waleed Ali
Developer
Builds Medical Records (vitals, prescriptions) and Billing (invoices, live totals, payments).
Y
Muhammad Yousaf
Developer / QA
Builds Pharmacy, Dashboard, Notifications, Reports and the browser self-test / final regression run.
Notes: Presenter: Abdullah. Each member owns one area so work does not collide. Umair is Product Owner, Abdullah Scrum Master.

## Slide 4
3. Product Backlog (prioritised)
# | ID | User story (short) | MoSCoW | Pts | Sprint 1
1 | PB-17 | Verified database design | Must | 8 | Yes
2 | PB-01 | Secure login | Must | 5 | Yes
3 | PB-02 | Patient register / edit / search | Must | 8 | Yes
4 | PB-04 | Doctors and departments | Must | 5 | Yes
5 | PB-06 | Book appointments, no double-booking | Must | 8 | Yes
6 | PB-07 | Medical records with vitals | Must | 8 | Yes
7 | PB-09 | Invoices, live totals, payments | Must | 8 | Yes
8 | PB-10 | Medicine stock and expiry alerts | Must | 5 | Yes
9 | PB-11 | Dispensing reduces stock | Must | 5 | Yes
10 | PB-18 | Automatic tests | Must | 5 | Yes
19 | PB-19 | Role-based access | Should | 8 | Later
20 | PB-20 | SMS / email reminders | Could | 5 | Later
21 | PB-21 | Invoice PDF export | Could | 3 | Later
22 | PB-22 | PostgreSQL + online hosting | Won't | 8 | Later
Ranks 11 to 18 (Should / Could stories, 28 pts) are also in Sprint 1; see the tool.
Notes: Presenter: Umair (Product Owner). Show the Backlog view in the tool. Order = dependencies first, then Must, Should, Could. Items 19-22 stay in the backlog for later sprints.

## Slide 5
4. Sprint Goal and duration
Deliver a working, testable HMS Increment: a staff member can log in and manage patients, doctors, appointments (no double-booking), medical records, billing and pharmacy stock, with every change stored in the SQLite database and covered by automatic tests.
14 days
19 Oct 2026 - 01 Nov 2026
166 h
44 tasks
93 pts
18 user stories
31 Oct / 1 Nov
Review / Retrospective
Definition of Done
Code works in Chrome/Edge against the real database (no localStorage data).
Browser validation, server rule and database constraint all behave as specified.
Acceptance criteria demonstrated to the Product Owner.
Automatic tests pass (tests/test_api.py, HMS_DB/verify_schema.py, selftest.html).
Another team member has reviewed the code (In Review column) before Done.
Notes: Presenter: Umair. Read the goal. 14 days, 166 hours of tasks for 5 people, review 31 Oct, retrospective 1 Nov. Definition of Done is on the right.

## Slide 6
5. Sprint Backlog: 18 user stories
ID | Story | Pts | Owners
PB-17 | Verified database design | 8 | Abdullah
PB-01 | Secure login | 5 | Abdullah, Umair
PB-02 | Patient register / edit / search | 8 | Umair
PB-04 | Doctors and departments | 5 | Talha
PB-06 | Book appointments, no double-booking | 8 | Abdullah, Talha
PB-07 | Medical records with vitals | 8 | Waleed
PB-09 | Invoices, live totals, payments | 8 | Waleed
PB-10 | Medicine stock and expiry alerts | 5 | Yousaf
PB-11 | Dispensing reduces stock | 5 | Yousaf
ID | Story | Pts | Owners
PB-18 | Automatic tests | 5 | Abdullah, Yousaf
PB-03 | Patient profile timeline | 5 | Umair
PB-05 | Doctor schedules, available today | 3 | Talha
PB-08 | Prescriptions in a visit | 3 | Waleed
PB-12 | Dashboard with alerts | 5 | Talha, Yousaf
PB-15 | Reports | 3 | Yousaf
PB-16 | Audit log | 3 | Abdullah
PB-13 | Notifications (read / unread) | 3 | Yousaf
PB-14 | Global search | 3 | Umair
Every story has acceptance criteria and at least two tasks of 2-7 hours.
Notes: Presenter: Umair. Open the Sprint Backlog in the tool. Each story has acceptance criteria written by the Product Owner and tasks owned by team members.

## Slide 7
5. Acceptance criteria (key stories)
PB-02 Patient register / edit / search
Required fields (first name, phone, date of birth) and formats are validated before saving.
A saved patient appears as a new row in the patients table.
Deleting a patient who has appointments is refused by the database (foreign key RESTRICT).
PB-06 Book appointments, no double-booking
Doctor list depends on the chosen department; time slots are offered for the chosen date.
Selecting an already booked slot shows a warning in the form.
Even if the form is bypassed, the database refuses two active appointments for the same doctor, date and time.
PB-09 Invoices, live totals, payments
Invoice supports several item rows; subtotal, discount, tax and total update live.
Items are stored as separate rows; total is computed by a view, never stored.
Payment status (unpaid / partial / paid) is saved and shown.
PB-11 Dispensing reduces stock
Dispensing writes a history row and reduces medicines.quantity.
Dispensing more than the available stock is refused by the server.
Notes: Presenter: Umair. Pick two stories and read the criteria. Say how each will be tested in the Sprint Review.

## Slide 8
6. Task breakdown and allocation
Abdullah
Database & Backend
9 tasks | 35 h
7 done (30 h)
Design 16-table schema with keys and CHECK constraints
Draw ER diagram and write sample_data.sql
Write verify_schema.py and database report
server.py: web server, JSON API skeleton, login with salted hash
Umair
Patients & Search
9 tasks | 33 h
7 done (29 h)
Login page UI with validation messages
Patient form + browser validation
Patient list: search, filter, edit, delete with FK refusal
Server patient endpoints and storage.js mapping
Talha
Doctors & Appointments
9 tasks | 33 h
7 done (28 h)
Doctor form and list with department filter
Server doctor + department endpoints
Weekly schedule rows and 'Available today' filter
Doctor profile page
Waleed
Records & Billing
8 tasks | 32 h
7 done (30 h)
Medical record form with vitals, BP as two numbers
Vitals range validation and systolic > diastolic rule
Prescription rows inside a medical record
Patient history view and follow-up date
Yousaf
Pharmacy, Dashboard & QA
9 tasks | 33 h
8 done (31 h)
Medicine form and stock list
Expiry and low-stock warnings
Dispensing form that reduces stock and writes history
Server refusal when quantity exceeds stock
Notes: Presenter: Abdullah. Each story is cut into tasks of 2-7 hours. Workload is balanced: 32-35 hours each. Done tasks are spread across all five members.

## Slide 9
7. Scheduling and dependencies
19
20
21
22
23
24
25
26
27
28
29
30
31
1
Oct 19 - Nov 1
Database and login
6 tasks
Patients and search
6 tasks
Doctors
4 tasks
Appointments
5 tasks
Medical records
4 tasks
Billing
3 tasks
Pharmacy
4 tasks
Dashboard and reports
4 tasks
Testing
3 tasks
Snapshot 25 Oct
Critical path: T-01 schema > T-04 server and login > module tasks > T-47 browser self-test > T-48 final regression run
Notes: Presenter: Talha. Bars show planned start to due date for each area. The database and server (T-01 to T-04) come first because every module depends on them. Critical path is on the bottom line.

## Slide 10
7. Estimates and burndown
Chart: Hours per member
| Abdullah | Umair | Talha | Waleed | Yousaf
Done (h) | 30 | 29 | 28 | 30 | 31
Remaining (h) | 5 | 4 | 5 | 2 | 2
Chart: Burndown (hours remaining)
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01
Ideal | 166 | 153.2 | 140.5 | 127.7 | 114.9 | 102.2 | 89.4 | 76.6 | 63.8 | 51.1 | 38.3 | 25.5 | 12.8 | 0
Actual | 163 | 157 | 149 | 120 | 92 | 44 | 18
Notes: Presenter: Talha. 166 hours committed, 148 done at the snapshot. Hours per person are balanced. Burndown is below the ideal line, meaning the team is ahead of plan; remaining items are review, QA and board administration.

## Slide 11
8. Scrum Board (snapshot 25 Oct)
To Do (2)
T-09 Import backlog and board into Jira/GitHub Projects, share workspace link
Abdullah | 2 h
T-18 Product Owner acceptance of the Increment at Sprint Review
Umair | 2 h
In Progress (3)
T-08 Sprint admin: planning, daily scrum notes, keep board current
Abdullah | 3 h
T-28 Dashboard 'today's schedule' widget
Talha | 3 h
T-48 Final regression run on a clean machine; save results files
Yousaf | 2 h
In Review (3)
T-17 Quick View modal for a patient
Umair | 2 h
T-27 Cancel / complete appointment status changes
Talha | 2 h
T-37 Peer code review of records and billing modules
Waleed | 2 h
Done (36)
7
Abdullah | 30 h
7
Umair | 29 h
7
Talha | 28 h
7
Waleed | 30 h
8
Yousaf | 31 h
Notes: Presenter: Waleed. SWITCH TO THE TOOL here and show the live board. Done column has 36 cards: 7 each for Abdullah, Umair, Talha, Waleed and 8 for Yousaf.

## Slide 12
9. Expected Sprint Increment
1
Login screen backed by the users table (salted password hash).
2
Patients: add, edit, view, search and delete; the database refuses deleting a patient with history.
3
Doctors: records, departments, weekly schedules, 'available today' filter.
4
Appointments: department > doctor > date > slot booking; double-booking blocked by form, server and database.
5
Medical records: vitals with range checks, prescriptions, patient history.
6
Billing: invoices with live totals, discount, tax and payment status.
7
Pharmacy: stock, expiry warnings, dispensing that reduces stock.
8
Dashboard, notifications, reports, global search and audit log.
9
Automatic tests: 86 API + 48 schema + 44 browser checks, all passing.
Notes: Presenter: Yousaf. Then run the live demo following HMS/PRESENTATION_GUIDE.md: login, add patient, FK refusal, book appointment, vitals validation, invoice, dispensing, audit log.

## Slide 13
10. Risks and challenges
Risk | Likelihood | Impact | Mitigation | Owner
Double-booking if two users book the same slot at the same moment | Medium | High | Unique index in the database as final guard; server checks first; test in test_api.py. | TA / AB
Data lost or inconsistent between browser, server and database | Medium | High | Single data layer (storage.js); foreign keys RESTRICT; Reset demo data button; audit_log. | AB
Modules depend on the database and server being ready first | High | Medium | Schema and server built first (T-01..T-04); others start after T-04; dependencies shown on the board. | AB
Team members fall behind or are unavailable | Medium | Medium | Daily scrum, tasks of 2-7 hours, pair review, Scrum Master reassigns blocked work. | AB
Scope creep (roles, SMS reminders, PDF export, PostgreSQL) | Medium | Medium | Kept in the Product Backlog (PB-19..PB-22); Product Owner decides; not in this Sprint. | UQ
Demo fails on another computer (Python version, port 8000 busy) | Low | High | Standard library only; start scripts for Win/Mac/Linux; port can be changed; rehearsal on a clean machine (T-48). | MY
Inconsistent validation between browser and server | Medium | Medium | Shared rules in validation.js; same rules re-checked in server.py and CHECK constraints; tests for each. | WA / UQ
Notes: Presenter: all members. Each member should be able to explain the risk in their own area. Owner column shows who watches it.

## Slide 14
Workspace and next steps
Project workspace link: PASTE-YOUR-JIRA-OR-GITHUB-PROJECTS-LINK-HERE
Show the Backlog, Sprint Backlog and Board live in the tool
Daily Scrum 10:00 (15 min); Sprint Review 31 Oct 2026; Retrospective 01 Nov 2026
Open items: T-09 workspace import, T-17/T-27/T-37 reviews, T-28 widget, T-48 final regression run, T-18 PO acceptance
All members are ready to justify the scope, estimates, allocations and deliverables
Thank you | Questions?
Notes: Presenter: all members. Open the project tool, then take questions. Each member answers about their own tasks.